## Sheet1
priority	change/improvement	concerned person	module	proposed approach/ details
high	add attack stats	rhishabh	notifications	use semantic ui stats, aggregate data from collected records, display stats
high	improve presentation	sahil	visualisation	put the buttons in single row (change margins to fit the buttons if not possible otherwise), resize the images to fit in the page, entire graph should be visible when page is opened
high	replace ajax requests with socket	sanika, rhishabh	dashboard	create socket between dashboard.js and php backend, use socket code of netlogs for reference for socket code in fe, find php code for socket
medium	reduce false alarm rates	sahil, rhishabh	ml model	recheck dataset created before, make changes in that
medium	add walls, improve smoothing	sanika	dashboard	add wall image in html (static), change number of values in array to improve smoothing (try more than 10 values in average)
medium	add pagination for tables	shruti	networkLogs, notification	find pagination code for semantic ui table, add it to tables, have fixed no of records in one page (eg 25), change page for more records
low	change home page		home	add content related to the project, not have any irrelevant information in the home page
low	change footers		layout	add content related to the project, not have any irrelevant information in the footer
low	show modules only on login	rhishabh	layout	display the modules (dash, vis, netlogs, notif) only after login (auth)
high	documentation	everyone	respective module	2 diagrams per module, description – will create template and send in the next couple of days