## Sheet1
Meeting no. | Date | Start Time | End Time | Duration | Location | Agenda | Discussions | Next meeting agenda | Members Present
1 | 2019-06-10 | 17:00 | 19:00 | 2:00 | Green Signal Restaurant | discuss project topic | rough ideas, overall project topics | more detailed project topics | everyone
2 | 2019-07-12 | 14:00 | 19:00 | 5:00 | Sanika's place | Decide topic, try GitHub organisation | brainstorming, got 5 topics, with priority, tested hello world with collaboration | create plan to make the project, create tentative timelines, assign roles | everyone
3 | 2019-08-10 | 10:00 | 17:00 | 7:00 | Sanika's place | fill project approval form | overview, module discussion, dataset, tested ddos with pinging | create timelines, assign roles | everyone
4 | 2019-09-25 | 10:00 | 17:15 | 7:15 | Sanika's place | fill project review form | divide topics and create form data | start implementation | everyone
5 | 2019-12-10 | 13:30 | 17:00 | 3:30 | Sanika's place | prepare for external review | slide allocation, survey paper proof read, web app model change, hardware requirements | create dataset | everyone
6 | 2020-01-19 | 11:30 | 17:00 | 5:30 | Rhishabh's place | create dataset | list of fields that can be considered, finding some with wireshark, but it's not detecting nodemcu data | create dataset | rhishabh, shruti
7 | 2020-01-26 | 14:00 | 18:00 | 4:00 | Shruti's office | review | create ppt | start web app, create dataset | rhishabh, shruti, sahil
8 | 2020-02-02 | 14:00 | 18:30 | 4:30 | Rhishabh's place | create dataset | divide work, set up github, create basic dataset, setup react and django apps in github repo | add more attacks, improve dataset, model | rhishabh, shruti, sahil
9 | 2020-02-09 | 15:30 | 20:00 | 4:30 | Rhishabh's place | new dataset, fe architecture | Added 2 attacks, 5 attacks total, created new dataset, designed home page, preproc of earlier dataset | start with backend, fe-be conn, real time data | rhishabh, shruti, sahil
10 | 2020-02-16 | 11:30 | 20:30 | 9:00 | Rhishabh's place | tshark dataset, model, fe architecture | created newest, biggest dataset, created real time model, distributed react components | optimise model, better detection, finish up with fe | everyone
11 | 2020-03-11 | 10:30 | 19:00 | 8:30 | Shruti's office | poster prep, distribution of combined webapp | created the poster, installed combined webapp on everyone's computer, started with ind pages | integrate all pages | everyone
12 | 2020-03-14 | 16:00 | 20:00 | 4:00 | Sanika's place | web app code | iot data car page, web socket tutorial | finish coding | everyone
13 | 2020-03-15 | 10:30 | 18:00 | 7:30 | Shruti's office | web sockets | finished backend - web socket setup | finish fe, integrate | rhishabh, shruti